## Product Backlog
Product Backlog
Id | Heading | As a.. | I want to .. | so that .. | Acceptance Criteria | Remarks | Priority | Status | Type | Project Id | Sprint No | Estimate (Hours) | Effort (Actual) | Owner | Status | Remarks
PB01 | Show post list | User | Show post list | I can see information of all post | display all post |  | 4 |  |  |  | 1 | 30 | 20 | thien | done | were all accomplished on schedule
PB02 | Show media video display | User | Show media video display | I can see all the video media of the show | display all media video |  | 4 |  |  |  | 2 | 30 | 25 | van vu | done | were all accomplished on schedule
PB03 | Show news list | User | show news | I can see information of all news | display all news |  | 4 |  |  |  | 1 | 30 | 23 | nhan | done | were all accomplished on schedule
PB04 | Comment | User | Comment | I can send comment for post | display comment section below the post |  | 1 |  |  |  | 1 | 15 | 15 | all member | done | were all accomplished on schedule
PB05 | Search post | User | Search post | I can search all post | display post follow keyword |  | 2 |  |  |  | 2 | 40 | 30 | all member | done | were all accomplished on schedule
PB06 | Register to find relatives | User | Register to find relatives | I can register to fine relatives | Display the registration form to find relatives |  | 4 |  |  |  | 2 | 45 | 40 | vinh | done | were all accomplished on schedule
PB07 | Advanced search | User | Advanced search | I can search using advanced method | Display advanced search box |  | 3 |  |  |  | 2 | 50 | 45 | thien | done | were all accomplished on schedule
PB08 | Search by lost situation | User | Search by lost situation | I can Search by lost situation | Display search box by lost situation |  | 4 |  |  |  | 3 | 45 | 40 | thien | done | were all accomplished on schedule
PB09 | Search for loved ones by pictures | User | Search for loved ones by pictures | I can search and identify a person through pictures | Display search box by lost pictures |  | 2 |  |  |  | 4 | 100 | 85 | vu | done | were all accomplished on schedule
PB10 | Searching for loved ones by objects | User | Searching for loved ones by objects | I can search through descriptions of familiar objects of the lost person | Display search box by lost object |  | 2 |  |  |  | 4 | 85 | 80 | vu | done | were all accomplished on schedule
PB11 | Show post list | Admin | show user all posts | I can find posts that work for me | login with admin account |  | 3 |  |  |  | 1 | 30 | 35 | vinh | done | were all accomplished on schedule
PB12 | edit post | Admin | edit all post | I can edit with user posts | login with admin account |  | 3 |  |  |  | 1 | 25 | 20 | vinh | done | were all accomplished on schedule
PB13 | delete post | Admin | delete post | I can delete with user posts | login with admin account |  | 3 |  |  |  | 1 | 25 | 20 | vinh | done | were all accomplished on schedule
PB14 | View all posts registered to find relatives | Admin | View all user's registrations to find relatives | I can confirm them or cancel | login with admin account |  | 3 |  |  |  | 2 | 30 | 30 | thien | done | were all accomplished on schedule
PB15 | add new post | Admin | Confirming 1 registration for finding relatives from a user | I can post it to the list of existing posts | login with admin account |  | 2 |  |  |  | 1 | 30 | 35 | thien | done | were all accomplished on schedule
PB16 | Show news list | Admin | Show news list | I can see the news | login with admin account |  | 4 |  |  |  | 3 | 25 | 25 | nhan | done | were all accomplished on schedule
PB17 | add new news | Admin | Add the new news | User can see the latest news | login with admin account |  | 4 |  |  |  | 3 | 25 | 20 | nhan | done | were all accomplished on schedule
PB18 | edit news | Admin | Edit news | provide accurate information to users | login with admin account |  | 3 |  |  |  | 3 | 20 | 20 | nhan | done | were all accomplished on schedule
PB19 | delete news | Admin | delete news | I can delete post that are no longer in use | login with admin account |  | 3 |  |  |  | 3 | 20 | 15 | nhan | done | were all accomplished on schedule
PB20 | show video media | Admin | Show video media | I can see media about relatives | login with admin account |  | 4 |  |  |  | 4 | 25 | 25 | van vu | done | were all accomplished on schedule
PB21 | add video media | Admin | Add video media | User can see relatives more clearly | login with admin account |  | 4 |  |  |  | 4 | 25 | 20 | van vu | done | were all accomplished on schedule
PB22 | edit video media | Admin | Edit video media | I can update accurate information | login with admin account |  | 4 |  |  |  | 4 | 25 | 30 | van vu | done | were all accomplished on schedule
PB23 | delete video media | Admin | Delete video media | I can delete error videos or videos I don't want to show | Delete video |  | 4 |  |  |  | 4 | 20 | 20 | van vu | done | were all accomplished on schedule
PB24 | Edit Advanced search | Admin | Edit Advanced search | I can edit Advanced search | Display edited Advances search |  | 2 |  |  |  | 3 | 30 | 25 | vu | done | were all accomplished on schedule
PB25 | add the search information according to the lost situation | Admin | Add the search information to the lost situation | I can add the search information to the lost situation | Display add information according the lost situation |  | 1 |  |  |  | 3 | 35 | 30 | vu | done | were all accomplished on schedule
PB26 | edit the search information according to the lost situation | Admin | Edit the search information to the lost situation | I can edit the search information to the lost situation | Display edited information according the lost situation |  | 1 |  |  |  | 3 | 30 | 25 | vu | done | were all accomplished on schedule
PB27 | restore photos to the past | Admin | Restore photos to the past | I can restore photos to the past | Display photos in the past |  | 3 |  |  |  | 4 | 40 | 45 | vu | inprocess | There are still some technical problems
PB28 | chat with admin | User | Chat with admin | I can Chat with admin | Display boxchat with admin |  | 1 |  |  |  | 4 | 25 | 25 | vinh | inprocess | There are still some technical problems
PB29 | chat by zalo | User | Chat by zalo | I can Chat by zalo | chat with zalo |  | 1 |  |  |  | 4 | 25 | 25 | nhan | inprocess | There are still some technical problems
PB30 | search news | User | Search news | I can Search all news | Display news follow search keyword |  | 2 |  |  |  | 2 | 20 | 15 | vu | done | were all accomplished on schedule
Note on M7: ====== ID#AAAAg0h_t9U jan samuelsson (2022-10-05 03:21:07) Fill in when a product backlog item has been assigned to a specific sprint. After a Sprint planning meeting is done.

## Main
Project | [5 empty] | Sprint Plan |  | Project #1
Id | Description | Start | End | Status | Remarks | Sprint # | Start | End | Status | Work / Estimates Committed | Work spent Delivered | Remarks
1 | Initial release | 2019-01-07 | 2019-03-15 | In Progress |  | 1 | 2023-03-13 | 2023-03-27 | done | 215 | 198 | were all accomplished on schedule
[6 empty] | 2 | 2023-03-28 | 2023-04-11 | done | 215 | 432 | were all accomplished on schedule
[6 empty] | 3 | 2023-04-12 | 2023-05-01 | done | 230 | 394 | were all accomplished on schedule
[6 empty] | 4 | 2023-05-02 | 2023-05-16 | infinish | 470 |  | problems with some applied technologies

## Sprint 1 Backlog
Project Name | Help Find lost loved ones
Module Name | Sprint 1
Development Team | HFLLO
Start Date | 13-Thg3-23
End Date | 27-Thg3-23
Sprint 1 Report
| No. | Member Name | Estimate | Actual
| 1 | Truong Quang Vu | 65 | 73
| 2 | Tong Tran Vinh | 51 | 67
| 3 | Le Van Thien | 39 | 42
| 4 | Tran Van Nhan | 50 | 52
| 5 | Huynh Van Vu | 23 | 30
| Total |  | 228 | 264
[5 empty] | Make new estimate when move from PB to SB |  |  |  |  | Only update one time. When task is done. You update with the estimate hours, NOT the hours you actually worked to finish the task.
Sprint Backlog |  |  | Add Owner when task is set to Ongoing | Update status during sprint
[7 empty] | Remaining work to be done. | Total number of hours you spent on the task. Your effort | Compare your estimate with the actual number of hours you spent on the task, your effort - = Spent less time than estimated
Estimate
Sprint Id | Backlog Id | Description | Owner | Status | Estimate (Hours) | Completed | Pending | Total effort | Effort vs. Actual | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Day 8 | Day 9 | Day 10 | Day 11 | Day 12 | Day 13 | Day 14 | Day 15
2022-01-01 |  | Create Sprint1Backlog | All Member | Done | 9 | 9 | 0 | 0 | -9 | Day 1: 7; Day 2: 2
2022-02-01 |  | Design Database | Vu | Done | 3 | 3 | 0 | 2 | -1 | Day 2: 3
2022-03-01 |  | Database Design Document | Vu | Done | 2 | 2 | 0 | 2 | 0 | Day 2: 2
2022-04-01 |  | Architecture Document | Vu | Done | 2 | 2 | 0 | 3 | 1 | Day 2: 2
2022-05-01 |  | Design UI Home Page | All Member | Done | 20 | 20 | 0 | 17 | -3 | Day 3: 10; Day 4: 10
2022-06-01 | PB01 | Design UI Show post list | Vu | Done | 15 | 15 | 0 | 15 | 0 | Day 3: 5; Day 4: 10
2022-07-01 | PB03 | Design UI Show news list | Nhan | Done | 10 | 10 | 0 | 11 | 1 | Day 3: 5; Day 4: 5
2022-08-01 | PB04 | Design UI Comment | All Member | Done | 7 | 7 | 0 | 7 | 0 | Day 4: 2; Day 5: 5
2022-09-01 | PB12,13,15 | Design UI CRUD post | Vu | Done | 10 | 10 | 0 | 9 | -1 | Day 5: 5; Day 6: 5
2022-10-01 |  | [FE] Code Home Page | All Member | Done | 25 | 25 | 0 | 20 | -5 | Day 6: 10; Day 7: 10; Day 8: 5
2022-11-01 | PB01 | [FE] Code Show post list | Thien | Done | 15 | 15 | 0 | 15 | 0 | Day 7: 5; Day 8: 10
2022-12-01 | PB01 | [BE] Code Show post list | Vu | Done | 10 | 10 | 0 | 7 | -3 | Day 8: 5; Day 9: 5
1.13 | PB03 | [FE] Code Show news list | Nhan | Done | 20 | 20 | 0 | 17 | -3 | Day 9: 10; Day 10: 10
1.14 | PB03 | [BE] Code Show news list | Vu | Done | 10 | 10 | 0 | 7 | -3 | Day 10: 5; Day 11: 5
1.15 | PB04 | [FE] Code Comment | All Member | Done | 10 | 10 | 0 | 10 | 0 | Day 10: 5; Day 11: 5
1.16 | PB04 | [BE] Code Comment | Vu | Done | 5 | 5 | 0 | 5 | 0 | Day 11: 5
1.17 | PB12,13,15 | [FE] Code CRUD post | All Member | Unfinished | 30 | 30 | 0 | 0 | -30 | Day 10: 10; Day 11: 10; Day 12: 10
1.18 | PB12,13,15 | [BE] Code CRUD post | Vu | Done | 10 | 10 | 0 | 6 | -4 | Day 11: 5; Day 12: 5
1.19 |  | Design Test Plan | Vinh | Done | 5 | 2 | 0 | 4 | -1 | Day 12: 5
1.20 |  | Test [FE] Code Home Page | Vinh | Done | 1 | 1 | 0 | 1 | 0 | bar: Day 13
1.21 |  | Test [FE] Code Show post list | Vinh | Done | 1 | 1 | 0 | 1 | 0 | bar: Day 13
1.22 |  | Test [BE] Code Show post list | Vinh | Done | 2 | 2 | 0 | 2 | -1 | bar: Day 13 to Day 14
1.23 |  | Test [FE] Code Show news list | Vinh | Done | 1 | 1 | 0 | 1 | 0 | bar: Day 14
1.24 |  | Test [BE] Code Show news list | Vinh | Done | 1 | 1 | 0 | 1 | 0 | bar: Day 14
1.25 |  | Test [FE] Code Comment | Vinh | Done | 1 | 1 | 0 | 1 | 0 | bar: Day 14
1.26 |  | Test [BE] Code Comment | Vinh | Done | 1 | 1 | 0 | 1 | 0 | bar: Day 15
1.27 |  | Test [FE] Code CRUD post | Vinh | Done | 1 | 1 | 0 | 1 | 0 | bar: Day 15
1.28 |  | Test [BE] Code CRUD post | Vinh | Done | 1 | 0 | 0 | 1 | 0 | bar: Day 15
|  |  |  | Total | 228 | 224 | 0 | 161 | -67 | 7 | 9 | 20 | 27 | 10 | 15 | 15 | 20 | 15 | 30 | 30 | 20 | 3 | 4 | 3
|  |  |  | Burn down | [5 empty] | 221 | 212 | 192 | 165 | 155 | 140 | 125 | 105 | 90 | 60 | 30 | 10 | 7 | 3 | 0
Sprint Backlog
Actual
Sprint Id | Backlog Id | Description | Owner | Status | Actual (Hours) | Completed | Pending | Total effort | Effort vs. Estimate | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Day 8 | Day 9 | Day 10 | Day 11 | Day 12 | Day 13 | Day 14 | Day 15
2022-01-01 |  | Create Sprint1Backlog | All Member | Done | 9 | 9 | 0 | 0 | -9 | Day 1: 7; Day 2: 2
2022-02-01 |  | Design Database | Vu | Done | 5 | 5 | 0 | 2 | -3 | Day 1: 2; Day 2: 3
2022-03-01 |  | Database Design Document | Vu | Done | 4 | 4 | 0 | 2 | -2 | Day 1: 2; Day 2: 2
2022-04-01 |  | Architecture Document | Vu | Done | 2 | 2 | 0 | 3 | 1 | Day 2: 2
2022-05-01 |  | Design UI Home Page | All Member | Done | 20 | 20 | 0 | 17 | -3 | Day 3: 10; Day 4: 10
2022-06-01 | PB01 | Design UI Show post list | Vu | Done | 20 | 15 | 5 | 15 | -5 | Day 3: 5; Day 4: 10; Day 5: 5
2022-07-01 | PB03 | Design UI Show news list | Nhan | Done | 13 | 12 | 1 | 11 | -2 | Day 3: 5; Day 4: 5; Day 5: 3
2022-08-01 | PB04 | Design UI Comment | All Member | Done | 9 | 7 | 2 | 7 | -2 | Day 4: 2; Day 5: 5; Day 6: 2
2022-09-01 | PB12,13,15 | Design UI CRUD post | Vu | Done | 13 | 10 | 3 | 9 | -4 | Day 5: 5; Day 6: 5; Day 7: 3
2022-10-01 |  | [FE] Code Home Page | All Member | Done | 29 | 25 | 4 | 20 | -9 | Day 6: 10; Day 7: 10; Day 8: 5; Day 9: 4
2022-11-01 | PB01 | [FE] Code Show post list | Thien | Done | 15 | 15 | 0 | 15 | 0 | Day 6: 5; Day 7: 5; Day 8: 5
2022-12-01 | PB01 | [BE] Code Show post list | Vu | Done | 15 | 15 | 0 | 7 | -8 | Day 8: 5; Day 9: 5; Day 10: 5
1.13 | PB03 | [FE] Code Show news list | Nhan | Done | 20 | 20 | 0 | 17 | -3 | Day 9: 10; Day 10: 10
1.14 | PB03 | [BE] Code Show news list | Vu | Done | 10 | 10 | 0 | 7 | -3 | Day 10: 5; Day 11: 5
1.15 | PB04 | [FE] Code Comment | All Member | Done | 10 | 10 | 0 | 10 | 0 | Day 10: 5; Day 11: 5
1.16 | PB04 | [BE] Code Comment | Vu | Done | 10 | 10 | 0 | 5 | -5 | Day 11: 5; Day 12: 5
1.17 | PB12,13,15 | [FE] Code CRUD post | All Member | Unfinished | 30 | 0 | 30 | 0 | -30 | Day 10: 10; Day 11: 10; Day 12: 10
1.18 | PB12,13,15 | [BE] Code CRUD post | Vu | Done | 10 | 10 | 0 | 6 | -4 | Day 11: 5; Day 12: 5
1.19 |  | Design Test Plan | Vinh | Done | 10 | 5 | 0 | 4 | -1 | Day 12: 5; Day 13: 5
1.20 |  | Test [FE] Code Home Page | Vinh | Done | 1 | 1 | 0 | 1 | 0 | bar: Day 13
1.21 |  | Test [FE] Code Show post list | Vinh | Done | 1 | 1 | 0 | 1 | 0 | bar: Day 13
1.22 |  | Test [BE] Code Show post list | Vinh | Done | 2 | 2 | 0 | 2 | -1 | bar: Day 13 to Day 14
1.23 |  | Test [FE] Code Show news list | Vinh | Done | 1 | 1 | 0 | 1 | 0 | bar: Day 14
1.24 |  | Test [BE] Code Show news list | Vinh | Done | 1 | 1 | 0 | 1 | 0 | bar: Day 14
1.25 |  | Test [FE] Code Comment | Vinh | Done | 1 | 1 | 0 | 1 | 0 | bar: Day 14
1.26 |  | Test [BE] Code Comment | Vinh | Done | 1 | 1 | 0 | 1 | 0 | bar: Day 15
1.27 |  | Test [FE] Code CRUD post | Vinh | Done | 1 | 1 | 0 | 1 | 0 | bar: Day 15
1.28 |  | Test [BE] Code CRUD post | Vinh | Done | 1 | 0 | 0 | 1 | 0 | bar: Day 15
|  |  |  | Total | 264 | 213 | 45 | 161 | -103 | 11 | 9 | 20 | 27 | 18 | 22 | 18 | 15 | 19 | 35 | 30 | 25 | 8 | 4 | 3
|  |  |  | Burn down | [5 empty] | 253 | 244 | 224 | 197 | 179 | 157 | 139 | 124 | 105 | 70 | 40 | 15 | 7 | 3 | 0
[9 empty] | Estimate | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Day 8 | Day 9 | Day 10 | Day 11 | Day 12 | Day 13 | Day 14 | Day 15
[8 empty] | Estimate | 228 | 221 | 212 | 192 | 165 | 155 | 140 | 125 | 105 | 90 | 60 | 30 | 10 | 7 | 3 | 0
[8 empty] | Actual | 228 | 253 | 244 | 224 | 197 | 179 | 157 | 139 | 124 | 105 | 70 | 40 | 15 | 7 | 3 | 0

## Sprint 1 Reports
Reports & Dashboards
Burn down Chart

## Sprint 2 Backlog
Project Name | Help Find lost loved ones
Module Name | Sprint 1
Development Team | HFLLO
Start Date | 28-Thg3-23
End Date | 11-Thg4-23
Sprint 1 Report
| No. | Member Name | Estimate | Actual
| 1 | Truong Quang Vu | 43 | 71
| 2 | Tong Tran Vinh | 50 | 56
| 3 | Le Van Thien | 50 | 63
| 4 | Tran Van Nhan | 35 | 35
| 5 | Huynh Van Vu | 22 | 38
| Total |  | 200 | 263
[5 empty] | ESTIMATE |  |  |  |  | Only update one time. When task is done. You update with the estimate hours, NOT the hours you actually worked to finish the task.
Sprint Backlog
Sprint Id | Backlog Id | Description | Owner | Status | Estimate (Hours) | Completed | Pending | Total effort | Effort vs. Estimate | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Day 8 | Day 9 | Day 10 | Day 11 | Day 12 | Day 13 | Day 14 | Day 15
2022-01-02 |  | Create Sprint2Backlog | All Member | Done | 10 | 10 | 0 | 10 | 0 | Day 1: 10
2022-02-02 |  | [FE] Code CRUD post | Thien | Done | 20 | 20 | 0 | 20 | 0 | Day 2: 10; Day 3: 10
2022-03-02 |  | Testing & Fix Bug For Sprint1 | All Member | Done | 5 | 5 | 0 | 4 | -1 | Day 2: 5
2022-04-02 | PB02 | Design UI Show media video display | Nhan | Done | 2 | 2 | 0 | 2 | 0 | Day 2: 2
2022-05-02 | PB05 | Design UI Search post | Van Vu | Done | 2 | 2 | 0 | 2 | 0 | Day 3: 2
2022-06-02 | PB06 | Design UI Register to find relatives | Van Vu | Done | 2 | 2 | 0 | 1 | -1 | Day 3: 2
2022-07-02 | PB07 | Design UI Advanced search | Vinh | Done | 2 | 2 | 0 | 1 | -1 | Day 3: 2
2022-08-02 | PB14 | Design UI View all posts registered to find relatives | Vu | Done | 2 | 2 | 0 | 2 | 0 | Day 3: 2
2022-09-02 | PB30 | Design UI search news | Thien | Done | 7 | 7 | 0 | 1 | -6 | Day 3: 5; Day 4: 2
2022-10-02 | PB02 | [FE] Code Show media video display | Van Vu | Done | 15 | 15 | 0 | 12 | -3 | Day 4: 10; Day 5: 5
2022-11-02 | PB02 | [BE] Code Show media video display | Vu | Done | 10 | 10 | 0 | 8 | -2 | Day 5: 5; Day 6: 5
2022-12-02 | PB05 | [FE] Code Search post | Thien | Done | 10 | 10 | 0 | 10 | 0 | Day 5: 5; Day 6: 5
2.13 | PB05 | [BE] Code Search post | Van Vu | Done | 3 | 3 | 0 | 2 | -1 | Day 6: 3
2.14 | PB06 | [FE] Code Register to find relatives | Vinh | Done | 20 | 25 | -5 | 20 | 0 | Day 6: 10; Day 7: 5; Day 8: 5
2.15 | PB06 | [BE] Code Register to find relatives | Vu | Done | 10 | 15 | -5 | 13 | 3 | Day 7: 5; Day 8: 5
2.16 | PB14 | [FE] Code View all posts registered to find relatives | Vinh | Unfinish | 25 | 25 | 0 | 0 | -25 | Day 8: 10; Day 9: 10; Day 10: 5
2.17 | PB14 | [BE] Code View all posts registered to find relatives | Vu | Done | 10 | 10 | 0 | 9 | -1 | Day 9: 5; Day 10: 5
2.18 | PB30 | [FE] Code search news | Nhan | Done | 15 | 15 | 0 | 10 | -5 | Day 10: 10; Day 11: 5
2.19 | PB30 | [BE] Code search news | Vu | Done | 5 | 5 | 0 | 4 | -1 | Day 11: 5
2.20 |  | Design Test Plan | Nhan | Done | 15 | 15 | 0 | 10 | -5 | Day 11: 10; Day 12: 5
2.21 |  | Test [FE] Code Show media video display | Thien | Done | 1 | 1 | 0 | 1 | 0 | bar: Day 13
2.22 |  | Test [BE] Code Show media video display | Thien | Done | 1 | 1 | 0 | 1 | 0 | bar: Day 13
2.23 |  | Test [FE] Code Search post | Thien | Done | 1 | 1 | 0 | 1 | 0 | bar: Day 13
2.24 |  | Test [BE] Code Search post | Thien | Done | 1 | 1 | 0 | 1 | 0 | bar: Day 14
2.25 |  | Test [FE] Code Register to find relatives | Thien | Done | 1 | 1 | 0 | 1 | 0 | bar: Day 14
2.26 |  | Test [BE] Code Register to find relatives | Thien | Done | 1 | 1 | 0 | 1 | 0 | bar: Day 14
2.27 |  | Test [FE] Code View all posts registered to find relatives | Thien | Done | 1 | 1 | 0 | 1 | 0 | bar: Day 14
2.28 |  | Test [BE] Code View all posts registered to find relatives | Thien | Done | 1 | 1 | 0 | 1 | 0 | bar: Day 15
2.29 |  | Test [FE] Code search news | Thien | Done | 1 | 1 | 0 | 1 | 0 | bar: Day 15
2.30 |  | Test [BE] Code search news | Thien | Done | 1 | 1 | 0 | 1 | 0 | bar: Day 15
|  |  |  | Total | 200 | 210 | -10 | 142 | -58 | 10 | 17 | 23 | 12 | 15 | 23 | 10 | 20 | 15 | 20 | 20 | 5 | 3 | 4 | 3
|  |  |  | Burn down | 200 | 210 | -10 |  |  | 190 | 173 | 150 | 138 | 123 | 100 | 90 | 70 | 55 | 35 | 15 | 10 | 7 | 3 | 0
ACTUAL
Sprint Id | Backlog Id | Description | Owner | Status | Estimate (Hours) | Completed | Pending | Total effort | Effort vs. Estimate | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Day 8 | Day 9 | Day 10 | Day 11 | Day 12 | Day 13 | Day 14 | Day 15
2022-01-02 |  | Create Sprint2Backlog | All Member | Done | 10 | 10 | 0 | 10 | 0 | Day 1: 10
2022-02-02 |  | [FE] Code CRUD post | Thien | Done | 25 | 25 | 0 | 25 | 0 | Day 1: 10; Day 2: 10; Day 3: 5
2022-03-02 |  | Testing & Fix Bug For Sprint1 | All Member | Done | 7 | 7 | 0 | 4 | -3 | Day 2: 5; Day 3: 2
2022-04-02 | PB02 | Design UI Show media video display | Nhan | Done | 6 | 6 | 0 | 2 | -4 | Day 2: 4; Day 3: 2
2022-05-02 | PB05 | Design UI Search post | Van Vu | Done | 6 | 6 | 0 | 2 | -4 | Day 2: 4; Day 3: 2
2022-06-02 | PB06 | Design UI Register to find relatives | Van Vu | Done | 3 | 3 | 0 | 1 | -2 | Day 3: 2; Day 4: 1
2022-07-02 | PB07 | Design UI Advanced search | Vinh | Done | 3 | 3 | 0 | 1 | -2 | Day 3: 2; Day 4: 1
2022-08-02 | PB14 | Design UI View all posts registered to find relatives | Vu | Done | 8 | 8 | 0 | 2 | -6 | Day 3: 4; Day 4: 4
2022-09-02 | PB30 | Design UI search news | Thien | Done | 15 | 15 | 0 | 1 | -14 | Day 3: 10; Day 4: 5
2022-10-02 | PB02 | [FE] Code Show media video display | Van Vu | Done | 20 | 20 | 0 | 22 | 2 | Day 4: 10; Day 5: 10
2022-11-02 | PB02 | [BE] Code Show media video display | Vu | Done | 10 | 10 | 0 | 12 | 2 | Day 5: 5; Day 6: 5
2022-12-02 | PB05 | [FE] Code Search post | Thien | Done | 10 | 10 | 0 | 10 | 0 | Day 5: 5; Day 6: 5
2.13 | PB05 | [BE] Code Search post | Vu | Done | 15 | 15 | 0 | 2 | -13 | Day 5: 5; Day 6: 5; Day 7: 5
2.14 | PB06 | [FE] Code Register to find relatives | Vinh | Done | 25 | 25 | 0 | 20 | -5 | Day 6: 10; Day 7: 10; Day 8: 5
2.15 | PB06 | [BE] Code Register to find relatives | Vu | Done | 15 | 15 | 0 | 13 | -2 | Day 7: 10; Day 8: 5
2.16 | PB14 | [FE] Code View all posts registered to find relatives | Vinh | Unfinish | 25 | 25 | 0 | 0 | -25 | Day 8: 10; Day 9: 10; Day 10: 5
2.17 | PB14 | [BE] Code View all posts registered to find relatives | Vu | Done | 10 | 10 | 0 | 9 | -1 | Day 9: 5; Day 10: 5
2.18 | PB30 | [FE] Code search news | Nhan | Done | 15 | 15 | 0 | 10 | -5 | Day 10: 10; Day 11: 5
2.19 | PB30 | [BE] Code search news | Vu | Done | 15 | 15 | 0 | 4 | -11 | Day 10: 10; Day 11: 5
2.20 |  | Design Test Plan | Nhan | Done | 10 | 10 | 0 | 10 | 0 | Day 11: 5; Day 12: 5
2.21 |  | Test [FE] Code Show media video display | Thien | Done | 1 | 1 | 0 | 1 | 0 | bar: Day 13
2.22 |  | Test [BE] Code Show media video display | Thien | Done | 1 | 1 | 0 | 1 | 0 | bar: Day 13
2.23 |  | Test [FE] Code Search post | Thien | Done | 1 | 1 | 0 | 1 | 0 | bar: Day 13
2.24 |  | Test [BE] Code Search post | Thien | Done | 1 | 1 | 0 | 1 | 0 | bar: Day 14
2.25 |  | Test [FE] Code Register to find relatives | Thien | Done | 1 | 1 | 0 | 1 | 0 | bar: Day 14
2.26 |  | Test [BE] Code Register to find relatives | Thien | Done | 1 | 1 | 0 | 1 | 0 | bar: Day 14
2.27 |  | Test [FE] Code View all posts registered to find relatives | Thien | Done | 1 | 1 | 0 | 1 | 0 | bar: Day 14
2.28 |  | Test [BE] Code View all posts registered to find relatives | Thien | Done | 1 | 1 | 0 | 1 | 0 | bar: Day 15
2.29 |  | Test [FE] Code search news | Thien | Done | 1 | 1 | 0 | 1 | 0 | bar: Day 15
2.30 |  | Test [BE] Code search news | Thien | Done | 1 | 1 | 0 | 1 | 0 | bar: Day 15
|  |  |  | Total | 263 | 263 | 0 | 161 | -102 | 20 | 23 | 29 | 21 | 25 | 25 | 25 | 20 | 15 | 30 | 15 | 5 | 3 | 4 | 3
|  |  |  | Burn down | 263 | 263 |  |  |  | 243 | 220 | 191 | 170 | 145 | 120 | 95 | 75 | 60 | 30 | 15 | 10 | 7 | 3 | 0
[8 empty] | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Day 8 | Day 9 | Day 10 | Day 11 | Day 12 | Day 13 | Day 14 | Day 15
[6 empty] | Estimate | 210 | 190 | 173 | 150 | 138 | 123 | 100 | 90 | 70 | 55 | 35 | 15 | 10 | 7 | 3 | 0
[6 empty] | Actual | 210 | 243 | 220 | 191 | 170 | 145 | 120 | 95 | 75 | 60 | 30 | 15 | 10 | 7 | 3 | 0

## Sprint 2 Reports
Reports & Dashboards
Burn down Chart

## Sprint 3 Backlog
Project Name | Help Find lost loved ones
Module Name | Sprint 3
Development Team | HFLLO
Start Date | 12-Thg4-23
End Date | 1-Thg5-23
Sprint 3 Report
| No. | Member Name | Estimate | Actual
| 1 | Truong Quang Vu | 90 | 100
| 2 | Tong Tran Vinh | 75 | 80
| 3 | Le Van Thien | 73 | 75
| 4 | Tran Van Nhan | 70 | 75
| 5 | Huynh Van Vu | 65 | 70
| Total |  | 373 | 400
|  |  | Add Owner when task is set to Ongoing | Update status during sprint | Make new estimate when move from PB to SB |  | Remaining work to be done. | Total number of hours you spent on the task. Your effort | Compare your estimate with the actual number of hours you spent on the task, your effort - = Spent less time than estimated | Only update one time. When task is done. You update with the estimate hours, NOT the hours you actually worked to finish the task.
Sprint Backlog
Estimate
Sprint Id | Backlog Id | Description | Owner | Status | Estimate (Hours) | Completed | Pending | Total effort | Effort vs. Estimate | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Day 8 | Day 9 | Day 10 | Day 11 | Day 12 | Day 13 | Day 14 | Day 15 | Day 16 | Day 17 | Day 18 | Day 19 | Day 20
2022-01-03 |  | Create Sprint3 Backlog | All Member | Done | 15 | 15 | 0 | 12 | -3 | Day 1: 10
2022-02-03 |  | [FE] Code View all posts registered to find relatives | Vinh | Done | 20 | 20 | 0 | 15 | -5 | Day 1: 5
2022-04-03 |  | Testing & Fix Bug For Sprint2 | All Member | Done | 10 | 10 | 0 | 12 | 2
2022-05-03 |  | Design UI Search by lost situation | Vinh | Done | 20 | 5 | 15 | 6 | -14 | Day 1: 5
2022-06-03 |  | Design UI Show news list | Nhan | Done | 8 | 5 | 3 | 5 | -3 | Day 2: 5; Day 3: 5
2022-07-03 |  | Design UI CRUD news | Nhan | Done | 10 | 5 | 5 | 5 | -5 | Day 2: 5
2022-08-03 |  | Design UI add the search information according to the lost situation | Vinh | Done | 5 | 5 | 0 | 5 | 0 | Day 2: 5
2022-09-03 |  | Design UI edit the search information according to the lost situation | Vinh | Done | 10 | 5 | 5 | 4 | -6 | Day 2: 5
2022-10-03 |  | [FE] Code Search by lost situation | Vinh | Done | 20 | 15 | 5 | 10 | -10 | Day 3: 10; Day 4: 10
2022-11-03 |  | [BE] Code Search by lost situation | Vu | Done | 5 | 5 | 0 | 5 | 0 | Day 3: 5; Day 4: 5; Day 5: 5; Day 6: 5; Day 7: 5; Day 8: 5
2022-12-03 |  | [FE] Code Show news list | Nhan | Done | 20 | 20 | 0 | 15 | -5 | Day 3: 5; Day 4: 5; Day 5: 12; Day 6: 5
3.13 |  | [BE] Code Show news list | Vu | Done | 15 | 5 | 10 | 4 | -11 | Day 4: 5; Day 5: 5; Day 6: 5; Day 7: 5; Day 8: 5; Day 9: 5; Day 10: 5
3.14 |  | [FE] Code CRUD news | Nhan | Infinish | 30 | 0 | 30 | 27 | -3 | Day 6: 5; Day 7: 5; Day 8: 5; Day 9: 5
3.15 |  | [BE] Code CRUD news | Vu | Done | 20 | 10 | 10 | 7 | -13 | Day 10: 5; Day 11: 5; Day 12: 5
3.16 |  | [FE] Code add the search information according to the lost situation | Thien | Infinish | 25 | 0 | 25 | 20 | -5 | Day 7: 5
3.17 |  | [BE] Code add the search information according to the lost situation | Vu | Infinish | 10 | 0 | 10 | 9 | -1 | Day 11: 10; Day 12: 10
3.18 |  | [FE] Code edit the search information according to the lost situation | Thien | Infinish | 25 | 0 | 25 | 20 | -5 | Day 8: 5
3.19 |  | [BE] Code edit the search information according to the lost situation | Vu | Infinish | 20 | 0 | 20 | 10 | -10 | Day 13: 5
3.20 |  | Design Test Plan | Thien | Done | 15 | 10 | 5 | 9 | -6 | Day 10: 5
3.21 |  | Test Search by lost situation | All Member | Done | 10 | 10 | 0 | 0 | 0 | Day 13: 5
3.22 |  | Test Show news list | All Member | Done | 10 | 10 | 0 | 0 | 0 | Day 15: 5
3.23 |  | Test CRUD news | All Member | Done | 10 | 10 | 0 | 0 | 0 | Day 13: 5
3.24 |  | Test add the search information according to the lost situation | All Member | Done | 10 | 10 | 0 | 0 | 0 | Day 13: 10; Day 14: 10; Day 16: 10; Day 20: 10
3.25 |  | Test edit the search information according to the lost situation | All Member | Done | 10 | 10 | 0 | 0 | 0 | Day 16: 10; Day 17: 10; Day 18: 8; Day 20: 8
3.26 |  | Test Code add the search information according to the lost situation | All Member | Done | 10 | 10 | 0 | 0 | 0 | Day 18: 10; Day 19: 10; Day 20: 10
3.27 |  | Test Code edit the search information according to the lost situation | All Member | Done | 10 | 10 | 0 | 0 | 0 | Day 19: 10; Day 20: 10
|  |  |  | Total | 373 | 205 | 168 | 200 | -173 | 20 | 20 | 25 | 25 | 22 | 20 | 20 | 20 | 10 | 15 | 15 | 15 | 25 | 10 | 5 | 20 | 10 | 18 | 20 | 38
|  |  |  | Burn down | [5 empty] | 353 | 333 | 308 | 283 | 261 | 241 | 221 | 201 | 191 | 176 | 161 | 146 | 121 | 111 | 106 | 86 | 76 | 58 | 38 | 0
Actual
Sprint Id | Backlog Id | Description | Owner | Status | Actual (Hours) | Completed | Pending | Total effort | Effort vs. Estimate | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Day 8 | Day 9 | Day 10 | Day 11 | Day 12 | Day 13 | Day 14 | Day 15 | Day 16 | Day 17 | Day 18 | Day 19 | Day 20
2022-01-03 |  | Create Sprint3 Backlog | All Member | Done | 15 | 15 | 0 | 12 | -3 | Day 1: 10
2022-02-03 |  | [FE] Code View all posts registered to find relatives | Vinh | Done | 20 | 20 | 0 | 15 | -5 | Day 1: 5
2022-04-03 |  | Testing & Fix Bug For Sprint2 | All Member | Done | 10 | 10 | 0 | 12 | 2
2022-05-03 |  | Design UI Search by lost situation | Vinh | Done | 15 | 15 | 0 | 6 | -9 | Day 1: 5
2022-06-03 |  | Design UI Show news list | Nhan | Done | 10 | 10 | 0 | 5 | -5 | Day 2: 5; Day 3: 5
2022-07-03 |  | Design UI CRUD news | Nhan | Done | 15 | 15 | 0 | 5 | -10 | Day 2: 5
2022-08-03 |  | Design UI add the search information according to the lost situation | Vinh | Done | 20 | 20 | 0 | 5 | -15 | Day 2: 5
2022-09-03 |  | Design UI edit the search information according to the lost situation | Vinh | Done | 15 | 15 | 0 | 4 | -11 | Day 2: 5
2022-10-03 |  | [FE] Code Search by lost situation | Vinh | Done | 15 | 15 | 0 | 10 | -5 | Day 3: 10; Day 4: 10
2022-11-03 |  | [BE] Code Search by lost situation | Vu | Done | 15 | 15 | 0 | 5 | -10 | Day 3: 5; Day 4: 5; Day 5: 5; Day 6: 5; Day 7: 5; Day 8: 5
2022-12-03 |  | [FE] Code Show news list | Nhan | Done | 20 | 20 | 0 | 15 | -5 | Day 4: 5; Day 5: 10; Day 6: 5
3.13 |  | [BE] Code Show news list | Vu | Done | 20 | 20 | 0 | 4 | -16 | Day 5: 5; Day 6: 5; Day 7: 5; Day 8: 5; Day 9: 5; Day 10: 5
3.14 |  | [FE] Code CRUD news | Nhan | Infinish | 30 | 30 | 0 | 27 | -3 | Day 6: 5; Day 7: 5; Day 8: 5; Day 9: 5
3.15 |  | [BE] Code CRUD news | Vu | Done | 20 | 20 | 0 | 7 | -13 | Day 10: 5; Day 11: 5; Day 12: 5
3.16 |  | [FE] Code add the search information according to the lost situation | Thien | Infinish | 25 | 25 | 0 | 20 | -5 | Day 7: 5
3.17 |  | [BE] Code add the search information according to the lost situation | Vu | Infinish | 20 | 20 | 0 | 9 | -11 | Day 11: 10; Day 12: 10
3.18 |  | [FE] Code edit the search information according to the lost situation | Thien | Infinish | 25 | 25 | 0 | 20 | -5 | Day 8: 5
3.19 |  | [BE] Code edit the search information according to the lost situation | Vu | Infinish | 10 | 10 | 0 | 10 | 0 | Day 13: 5; Day 14: 5
3.20 |  | Design Test Plan | Thien | Done | 10 | 10 | 0 | 9 | -1 | Day 10: 10; Day 11: 10; Day 12: 10; Day 13: 10
3.21 |  | Test Search by lost situation | All Member | Done | 10 | 10 | 0 | 5 | -5 | Day 20: 10
3.22 |  | Test Show news list | All Member | Done | 10 | 10 | 0 | 6 | -4 | Day 15: 5; Day 20: 5
3.23 |  | Test CRUD news | All Member | Done | 10 | 10 | 0 | 4 | -6 | Day 20: 10
3.24 |  | Test add the search information according to the lost situation | All Member | Done | 10 | 10 | 0 | 2 | -8 | Day 20: 10
3.25 |  | Test edit the search information according to the lost situation | All Member | Done | 10 | 10 | 0 | 5 | -5 | Day 16: 10; Day 17: 10; Day 18: 10; Day 19: 10; Day 20: 10
3.26 |  | Test Code add the search information according to the lost situation | All Member | Done | 10 | 10 | 0 | 3 | -7 | Day 18: 10; Day 19: 10; Day 20: 10
3.27 |  | Test Code edit the search information according to the lost situation | All Member | Done | 10 | 10 | 0 | 5 | -5 | Day 19: 10; Day 20: 10
|  |  |  | Total | 400 | 400 | 0 | 230 | -170 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 10 | 20 | 25 | 25 | 15 | 5 | 5 | 10 | 10 | 20 | 30 | 65
|  |  |  | Burn down | [5 empty] | 380 | 360 | 340 | 320 | 300 | 280 | 260 | 240 | 230 | 210 | 185 | 160 | 145 | 140 | 135 | 125 | 115 | 95 | 65 | 0
[9 empty] | Estimate | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Day 8 | Day 9 | Day 10 | Day 11 | Day 12 | Day 13 | Day 14 | Day 15 | Day 16 | Day 17 | Day 18 | Day 19 | Day 20
[8 empty] | Estimate | 373 | 353 | 333 | 308 | 283 | 261 | 241 | 221 | 201 | 191 | 176 | 161 | 146 | 121 | 111 | 106 | 86 | 76 | 58 | 38 | 0
[8 empty] | Actual | 373 | 380 | 360 | 340 | 320 | 300 | 280 | 260 | 240 | 230 | 210 | 185 | 160 | 145 | 140 | 135 | 125 | 115 | 95 | 65 | 0

## Sprint 3 Reports
Reports & Dashboards
Burn down Chart

## Sprint 4 Backlog
Project Name | Help Find lost loved ones
Module Name | Sprint 4
Development Team | HFLLO
Start Date | 2-Thg5-23
End Date | 16-Thg5-23
Sprint 4 Report
| No. | Member Name | Estimate | Actual
| 1 | Truong Quang Vu | 98 | 114
| 2 | Tong Tran Vinh | 77 | 100
| 3 | Le Van Thien | 75 | 96
| 4 | Tran Van Nhan | 70 | 90
| 5 | Huynh Van Vu | 65 | 80
| Total |  | 385 | 480
[5 empty] | Make new estimate when move from PB to SB |  |  |  |  | Only update one time. When task is done. You update with the estimate hours, NOT the hours you actually worked to finish the task.
Sprint Backlog |  |  | Add Owner when task is set to Ongoing | Update status during sprint
[7 empty] | Remaining work to be done. | Total number of hours you spent on the task. Your effort | Compare your estimate with the actual number of hours you spent on the task, your effort - = Spent less time than estimated
Estimate
Sprint Id | Backlog Id | Description | Owner | Status | Estimate (Hours) | Completed | Pending | Total effort | Effort vs. Actual | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Day 8 | Day 9 | Day 10 | Day 11 | Day 12 | Day 13 | Day 14 | Day 15
2022-01-04 |  | Create Sprint4Backlog | All Member | Done | 15 | 15 | 0 | 9 | -6 | Day 1: 15
2022-02-04 |  | Design UI Search for loved ones by pictures | Vinh | Done | 5 | 5 | 0 | 6 | 1 | Day 1: 5
2022-03-04 |  | Design UI Searching for loved ones by objects | Thien | Done | 5 | 5 | 0 | 5 | 0 | Day 1: 5
2022-04-04 |  | Design UI show video media | Nhan | Done | 5 | 5 | 0 | 5 | 0 | Day 1: 5
2022-05-04 |  | Design UI CRUD video media | Nhan | Done | 10 | 10 | 0 | 5 | -5 | Day 2: 5; Day 3: 5
2022-06-04 |  | Design UI restore photos to the past | Vu | Done | 5 | 5 | 0 | 5 | 0 | Day 2: 5
2022-07-04 |  | Design UI chat with admin | Van Vu | Done | 5 | 5 | 0 | 35 | 30 | Day 2: 5
2022-08-04 |  | Design UI chat by zalo | Thien | Done | 5 | 5 | 0 | 7 | 2 | Day 2: 5
2022-09-04 |  | [FE] Code Search for loved ones by pictures | Thien | Done | 20 | 20 | 0 | 20 | 0 | Day 3: 10; Day 4: 10
2022-10-04 |  | [BE] Code Search for loved ones by pictures | Vu | Done | 40 | 40 | 0 | 65 | 25 | Day 2: 5; Day 3: 5; Day 4: 5; Day 5: 5; Day 6: 5; Day 7: 5; Day 8: 5; Day 9: 5
2022-11-04 |  | [FE] Code Searching for loved ones by objects | Thien | Done | 25 | 25 | 0 | 20 | -5 | Day 3: 5; Day 4: 5; Day 5: 10; Day 6: 5
2022-12-04 |  | [BE] Code Searching for loved ones by objects | Vu | Done | 40 | 40 | 0 | 60 | 20 | Day 4: 5; Day 5: 5; Day 6: 5; Day 7: 5; Day 8: 5; Day 9: 5; Day 10: 10
4.13 |  | [FE] Code CRUD video media | Van Vu | Done | 30 | 30 | 0 | 45 | 15 | Day 5: 10; Day 6: 5; Day 7: 5; Day 8: 5; Day 9: 5
4.14 |  | [BE] Code CRUD video media | Vu | Done | 30 | 30 | 0 | 50 | 20 | Day 10: 10; Day 11: 5; Day 12: 5; Day 13: 5; Day 14: 5
4.15 |  | [FE] Code restore photos to the past | Nhan | Done | 10 | 10 | 0 | 15 | 5 | Day 6: 5; Day 7: 5
4.16 |  | [BE] Code restore photos to the past | Vu | Done | 20 | 20 | 0 | 15 | -5 | Day 11: 10; Day 12: 10
4.17 |  | [FE] Code chat with admin | Vinh | Done | 10 | 10 | 0 | 10 | 0 | Day 7: 5; Day 8: 5
4.18 |  | [BE] Code chat with admin | Vu | Done | 15 | 15 | 0 | 15 | 0 | Day 13: 5; Day 14: 5; Day 15: 5
4.19 |  | [FE] Code chat by zalo | Nhan | Done | 10 | 10 | 0 | 10 | 0 | Day 10: 10
4.20 |  | [BE] Code chat by zalo | Vu | Done | 15 | 15 | 0 | 15 | 0 | Day 13: 5; Day 14: 5; Day 15: 5
4.21 |  | Design Test Plan | All Member | Done | 20 | 20 | 0 | 24 | 4 | Day 14: 10; Day 15: 10
4.22 |  | test feature for “Search for loved ones by pictures” | All Member | Done | 5 | 5 | 0 | 5 | 0 | Day 13: 5
4.23 |  | test feature for “Searching for loved ones by objects” | All Member | Done | 5 | 5 | 0 | 5 | 0 | Day 13: 5
4.24 |  | test feature for “show video media” | All Member | Done | 5 | 5 | 0 | 5 | 0 | Day 14: 5
4.25 |  | test feature for “add video media” | All Member | Done | 5 | 5 | 0 | 5 | 0 | Day 14: 5
4.26 |  | test feature for “edit video media” | All Member | Done | 5 | 5 | 0 | 5 | 0 | Day 14: 5
4.27 |  | test feature for “delete video media” | All Member | Done | 5 | 5 | 0 | 5 | 0 | Day 15: 5
4.28 |  | test feature for “restore photos to the past” | All Member | Done | 5 | 5 | 0 | 5 | 0 | Day 15: 5
4.29 |  | test feature for “chat with admin” | All Member | Done | 5 | 5 | 0 | 5 | 0 | Day 15: 5
4.30 |  | test feature for “chat by zalo” | All Member | Done | 5 | 5 | 0 | 5 | 0 | Day 15: 5
|  |  |  | Total | 385 | 385 | 0 | 446 | 61 | 30 | 25 | 25 | 25 | 30 | 25 | 25 | 20 | 15 | 30 | 15 | 15 | 25 | 40 | 40
|  |  |  | Burn down | [5 empty] | 355 | 330 | 305 | 280 | 250 | 225 | 200 | 180 | 165 | 135 | 120 | 105 | 80 | 40 | 0
Sprint Backlog
Actual
Sprint Id | Backlog Id | Description | Owner | Status | Actual (Hours) | Completed | Pending | Total effort | Effort vs. Estimate | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Day 8 | Day 9 | Day 10 | Day 11 | Day 12 | Day 13 | Day 14 | Day 15
2022-01-04 |  | Create Sprint4Backlog | All Member | Done | 15 | 15 | 0 | 9 | -6 | Day 1: 15
2022-02-04 |  | Design UI Search for loved ones by pictures | Vinh | Done | 5 | 5 | 0 | 6 | 1 | Day 1: 5
2022-03-04 |  | Design UI Searching for loved ones by objects | Thien | Done | 5 | 5 | 0 | 5 | 0 | Day 1: 5
2022-04-04 |  | Design UI show video media | Nhan | Done | 5 | 5 | 0 | 5 | 0 | Day 1: 5
2022-05-04 |  | Design UI CRUD video media | Nhan | Done | 10 | 10 | 0 | 5 | -5 | Day 2: 5; Day 3: 5
2022-06-04 |  | Design UI restore photos to the past | Vu | Done | 5 | 5 | 0 | 5 | 0 | Day 2: 5
2022-07-04 |  | Design UI chat with admin | Van Vu | Done | 5 | 5 | 0 | 35 | 30 | Day 2: 5
2022-08-04 |  | Design UI chat by zalo | Thien | Done | 5 | 5 | 0 | 7 | 2 | Day 2: 5
2022-09-04 |  | [FE] Code Search for loved ones by pictures | Thien | Done | 25 | 25 | 0 | 20 | -5 | Day 3: 15; Day 4: 10
2022-10-04 |  | [BE] Code Search for loved ones by pictures | Vu | Done | 65 | 80 | -15 | 65 | 0 | Day 2: 10; Day 3: 10; Day 4: 10; Day 5: 10; Day 6: 10; Day 7: 5; Day 8: 5; Day 9: 5
2022-11-04 |  | [FE] Code Searching for loved ones by objects | Thien | Done | 30 | 30 | 0 | 20 | -10 | Day 3: 5; Day 4: 10; Day 5: 10; Day 6: 5
2022-12-04 |  | [BE] Code Searching for loved ones by objects | Vu | Done | 60 | 60 | 0 | 60 | 0 | Day 4: 5; Day 5: 5; Day 6: 10; Day 7: 10; Day 8: 10; Day 9: 10; Day 10: 10
4.13 |  | [FE] Code CRUD video media | Van Vu | Done | 25 | 35 | -10 | 45 | 20 | Day 5: 5; Day 6: 5; Day 7: 5; Day 8: 5; Day 9: 5
4.14 |  | [BE] Code CRUD video media | Vu | Done | 50 | 50 | 0 | 50 | 0 | Day 10: 10; Day 11: 10; Day 12: 10; Day 13: 10; Day 14: 10
4.15 |  | [FE] Code restore photos to the past | Nhan | Done | 20 | 20 | 0 | 15 | -5 | Day 6: 10; Day 7: 10
4.16 |  | [BE] Code restore photos to the past | Vu | Done | 30 | 30 | 0 | 15 | -15 | Day 11: 15; Day 12: 15
4.17 |  | [FE] Code chat with admin | Vinh | Done | 10 | 10 | 0 | 10 | 0 | Day 7: 5; Day 8: 5
4.18 |  | [BE] Code chat with admin | Vu | Done | 20 | 20 | 0 | 15 | -5 | Day 13: 10; Day 14: 5; Day 15: 5
4.19 |  | [FE] Code chat by zalo | Nhan | Done | 10 | 10 | 0 | 10 | 0 | Day 10: 10
4.20 |  | [BE] Code chat by zalo | Vu | Done | 15 | 15 | 0 | 15 | 0 | Day 13: 5; Day 14: 5; Day 15: 5
4.21 |  | Design Test Plan | All Member | Done | 20 | 20 | 0 | 24 | 4 | Day 14: 10; Day 15: 10
4.22 |  | test feature for “Search for loved ones by pictures” | All Member | Done | 5 | 5 | 0 | 5 | 0 | Day 13: 5
4.23 |  | test feature for “Searching for loved ones by objects” | All Member | Done | 5 | 5 | 0 | 5 | 0 | Day 13: 5
4.24 |  | test feature for “show video media” | All Member | Done | 5 | 5 | 0 | 5 | 0 | Day 14: 5
4.25 |  | test feature for “add video media” | All Member | Done | 5 | 5 | 0 | 5 | 0 | Day 14: 5
4.26 |  | test feature for “edit video media” | All Member | Done | 5 | 5 | 0 | 5 | 0 | Day 14: 5
4.27 |  | test feature for “delete video media” | All Member | Done | 5 | 5 | 0 | 5 | 0 | Day 15: 5
4.28 |  | test feature for “restore photos to the past” | All Member | Done | 5 | 5 | 0 | 5 | 0 | Day 15: 5
4.29 |  | test feature for “chat with admin” | All Member | Done | 5 | 5 | 0 | 5 | 0 | Day 15: 5
4.30 |  | test feature for “chat by zalo” | All Member | Done | 5 | 5 | 0 | 5 | 0 | Day 15: 5
|  |  |  | Total | 480 | 505 | -25 | 446 | -34 | 30 | 30 | 35 | 35 | 30 | 40 | 35 | 25 | 20 | 30 | 25 | 25 | 35 | 45 | 40
|  |  |  | Burn down | [5 empty] | 450 | 420 | 385 | 350 | 320 | 280 | 245 | 220 | 200 | 170 | 145 | 120 | 85 | 40 | 0
[9 empty] | Estimate | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Day 8 | Day 9 | Day 10 | Day 11 | Day 12 | Day 13 | Day 14 | Day 15
[8 empty] | Estimate | 385 | 355 | 330 | 305 | 280 | 250 | 225 | 200 | 180 | 165 | 135 | 120 | 105 | 80 | 40 | 0
[8 empty] | Actual | 385 | 450 | 420 | 385 | 350 | 320 | 280 | 245 | 220 | 200 | 170 | 145 | 120 | 85 | 40 | 0

## Sprint 4 Reports
Reports & Dashboards
Burn down Chart

## Impediment
Impediments | [5 empty] | In charge of removing the impediment | Not started Ongoing Done
|  |  | Date | [5 empty] | Date
Id | Description | Raised By | Raised On | Sprint # | Impacted Backlog # | Owner | Status | Resolution | Resolved On

## Retrospective
In the retrospecitve meeting after each sprint you will identify/find many things to improve. That does not mean that you will do all the changes in the next sprint. Usually you do changes step by step. E.g. 1-3 changes in one sprint. Not more than that. So sometimes you find an improvement in one sprint and then in a much later sprint you will actually do the change.
Retrospective Log
Found in Sprint # | Impl. In Sprint # |  | Responsible for doing the improvement
Sprint # | Sprint # | Date | Owner | Start Doing (Improvement) | Continue Doing (What Went Well) | Stop Doing (Even better if) | Remarks

## References
References
External |  | Internal
Description | Link | Description | Link
Glossary & Terminology | https://www.scrumalliance.org/community/articles/2007/march/glossary-of-scrum-terms